## Sheet1
5 Month To-Do List
TASK | PRIORITY | STATUS | START DATE | DUE DATE | % COMPLETE | NOTES
Gutter replacement on RES and RHS | Normal | Not Started | TBD |  | 20% | $5006.00 PO#2220672
Playground fence repair | High | In Progress | 2022-01-11 | 2022-03-31 | 50% | Waiting on parts
Flooring in RES & RHS | High | Not Started | 2022-06-01 | 2022-07-01 | 20% | $22,115.00 PO#2220673
RES roof repair over preschool | High | Not Started | TBD |  | 20% | $2566.00 PO# 2220671
Sidewalk infront of RES | High | Not Started | TBD |  | 10% | 23000
Side trash room RHS | Normal | Not Started | TBD |  | 10% | 2000
2 new sinks in HS locker room | Normal | Not Started | TBD |  | 10% | 500
Tuck piont RES | Low | Not Started | TBD |  | 0% | Need Quotes
RHS chiminey repair | Low | Not Started | TBD |  | 0% | Need Quotes
Rear doors on sports center | Normal | Not Started | TBD |  | 10% | 6000
Swale tile and fill | Low | Not Started | TBD |  | 0% | Need Quotes
Perimator Fence on south and south east of football field | Low | Not Started | TBD |  | 0% | Need Quotes
Refill longump pits | High | In Progress | 2022-02-03 |  | 0% | Athletics
RES Heating | High | Not Started | TBD |  | 0%
AG paint room door | Normal | Not Started | TBD |  | 20% | $3780.00 PO# 2220657